## Sheet1
Joint Consortium for School Health Annual Work Plan 2020-21
Legend: This is a list of all activities developed and colour coded by seasons: Spring, Summer, Autumn, Winter. The cells with a light blue background colour each have a definition embedded.
JCSH Priorities:
· Mental well-being, COVID-19 crisis response, social-emotional learning, resiliency, anxiety, protective factors and disruptive behaviours;
· Problematic substance use, with a strong initial focus on vaping; and
· School food environment, including the alignment of healthy eating school food policies and priorities
...all addressed through the comprehensive school health approach.
***List of Abbreviations at bottom of table
ACTION # | DECISIONS/ACTIONS (WHAT) | PROCESSES (HOW) | RESPONSIBILITY (WHO) | STATUS/TARGET COMPLETION DATES (WHEN) | Goal 1: Providing Leadership |  |  |  | Goal 2: Capacity Through KDE |  |  |  | Goal 3: Promoting Innovation |  |  |  | Goal 4: M., E., & A.
[5 empty] | S1 | S2 | S3 | S4 | S1 | S2 | S3 | S4 | S1 | S2 | S3 | S4 | S1 | S2 | S3
1 | Letter to ACDME, DMoH |  | MC | bar: Goal 1: Providing Leadership S1
2 | CMEC, Health /P'n priorities |  | S, SHCC | bar: Goal 1: Providing Leadership S1; Goal 1: Providing Leadership S3
3 | CMEC Rep |  | MC | bar: Goal 1: Providing Leadership S1
4 | CMEC, PHN Meetings |  | MC | 2x year | bar: Goal 1: Providing Leadership S1
5 | JCSH Tools, Resources |  | SHCC | bar: Goal 1: Providing Leadership S2
6 | Cross-jurisdictional Updates |  | MC. SHCC | Ongoing | bar: Goal 1: Providing Leadership S2
7 | Budget Decisions |  | MC | bar: Goal 1: Providing Leadership S2
8 | Promote Current Resources |  | MC, SHCC, S | bar: Goal 1: Providing Leadership S2
9 | Share PT Policies |  | MC. SHCC | bar: Goal 1: Providing Leadership S2
10 | CSH-Based Summaries |  | S, SHCC | bar: Goal 1: Providing Leadership S2
11 | Fed Gov Teams to Meetings | Invitation | MC, SHCC | bar: Goal 1: Providing Leadership S3
12 | Post-Presentations Evals |  | S | bar: Goal 1: Providing Leadership S3
13 | PT Reps, FPT Tables |  | MC, SHCC | bar: Goal 1: Providing Leadership S3
14 | FPT Tables Connections |  | MC | bar: Goal 1: Providing Leadership S3
15 | ID Fed Initiatives' Tables |  | MC, SHCC, S | bar: Goal 1: Providing Leadership S3
16 | Jurisdictional Initiatives |  | MC, SHCC | bar: Goal 1: Providing Leadership S3
17 | Partners' Lists |  | MC, SHCC, S | bar: Goal 1: Providing Leadership S4
18 | Define JCSH Value-Add |  | MC, SHCC | bar: Goal 1: Providing Leadership S4
19 | Jurisdiction-specific NGOs |  | MC, SHCC, S | bar: Goal 1: Providing Leadership S4
20 | Update Comms Pieces |  | S, SHCC | bar: Goal 1: Providing Leadership S4
21 | Environmental Scans |  | S, SHCC, MC | bar: Goal 1: Providing Leadership S2; Goal 2: Capacity Through KDE S1; Goal 2: Capacity Through KDE S3; Goal 3: Promoting Innovation S1; Goal 3: Promoting Innovation S3
22 | Share Research, ID Gaps |  | S, SHCC, MC | bar: Goal 2: Capacity Through KDE S1
23 | Prog. Eval. Research |  | S, SHCC, MC | bar: Goal 2: Capacity Through KDE S1
| Clarification of Strategy |  | MC | bar: Goal 2: Capacity Through KDE S2
24 | CSH-diversity resource |  | SHCC, S | bar: Goal 2: Capacity Through KDE S3
25 | CSH checklist |  | SHCC, S | bar: Goal 2: Capacity Through KDE S3
26 | Partners-expertise |  | MC, SHCC, S | bar: Goal 2: Capacity Through KDE S3
27 | Ministries' Participation |  | MC, SHCC | bar: Goal 2: Capacity Through KDE S4
28 | Working Group Rep'n |  | Mc,SHCC | bar: Goal 2: Capacity Through KDE S4
29 | Ministries' Expertise |  | SHCC | bar: Goal 2: Capacity Through KDE S4
30 | Research/Interventions |  | S, MC, SHCC | bar: Goal 3: Promoting Innovation S1
31 | Emerging Trends Tracking |  | S | bar: Goal 3: Promoting Innovation S1
32 | Policies, Practice Template |  | SHCC, S | bar: Goal 3: Promoting Innovation S1
33 | Create Summaries |  | SHCC, S | bar: Goal 3: Promoting Innovation S1
34 | Evergreen Scans, Resources |  | S | bar: Goal 3: Promoting Innovation S2
35 | Share Juris'l Responses |  | MC, SHCC | bar: Goal 3: Promoting Innovation S2
36 | Trends - Private Side Website |  | S | bar: Goal 3: Promoting Innovation S2
| Clarification of Strategy |  | MC | bar: Goal 3: Promoting Innovation S3
37 | Research Funders |  | MC | bar: Goal 3: Promoting Innovation S3
38 | CIM Action Item |  | MC | bar: Goal 3: Promoting Innovation S3
| Clarification of Strategy |  | MC | bar: Goal 3: Promoting Innovation S4
39 | HBSC Relationship |  | MC, SHCC, S | bar: Goal 3: Promoting Innovation S4
40 | Workplan, Budget Timelines |  | MC | bar: Goal 1: Providing Leadership S2; Goal 4: M., E., & A. S1
41 | Staging Plan |  | MC, SHCC | bar: Goal 4: M., E., & A. S1
42 | Review 2019 Evaluation |  | MC, SHCC, S | bar: Goal 4: M., E., & A. S2
43 | Evaluation Framework |  | MC | bar: Goal 4: M., E., & A. S2
44 | Formative Evaluation | 2 years into Mandate | MC, SHCC, S | bar: Goal 4: M., E., & A. S2
45 | Summative Evaluation | 4 years into Mandate | MC, SHCC, S | bar: Goal 4: M., E., & A. S2
46 | MC-SHCC Relations |  | MC, SHCC | bar: Goal 4: M., E., & A. S3
47 | Evaluation Tool |  | MC, SHCC | bar: Goal 4: M., E., & A. S3
48 | Health, ED Engagement |  | MC, SHCC | bar: Goal 4: M., E., & A. S3
49 | Review Resource Sharing |  | MC, SHCC | bar: Goal 4: M., E., & A. S3
50 | Governance Review | Annual | MC | bar: Goal 4: M., E., & A. S3
51 | Track News Bundles |  | S | bar: Goal 4: M., E., & A. S3