## Sheet1
JCSH Operating Plan 2015-2020
GOAL | STRATEGY | INDICATORS | ACTION | 5-YEAR TARGET (2020) | PROGRESS TO DATE
LEADERSHIP | Support ministerial collaboration
|  | CBNs, Common messages | Develop comms materials | 1/issue ~ 5 per year | 20% | 20%
|  | CSH Research Highlights | Share research findings | 3/year | 20% | 20%
|  | JCSH Tables' balance | Ensure Health, ED voices | 30-50% from each | 25% | 25%
| Strengthen existing partnerships | Strong Existing Partnerships | Monitor partnership gaps | Annually | 30% | 30%
|  |  | Opportunities to align | ~4/year | 30% | 30%
|  |  | Criteria for Partnerships | 1/mandate | 50% | 50%
| Engage new partner organizations | New Partnerships | Inventory of new partners | 1/mandate | 60% | 60%
|  | Aligned goals | Enhance collaborations | Annually | 25% | 25%
|  | Northern, remote partnerships | Seek northern, remote partners |  | 0% | 0%
| Explore engagement additional sectors | Opportunities with govt sectors | Identify opportunities | Quarterly | 25% | 25%
|  | Opportunities for NGOs | Identify opportunities | Quarterly | 30% | 30%
| Strengthen inclusiveness | Equity Working Group | Develop and hold meetings | Quarterly meetings | 25% | 25%
|  | Equity Environmental Scan | Develop inventory of policies etc | Annual monitoring | 50% | 50%
|  | Equity lens to JCSH tools | Develop equity checklist | Annual monitoring | 0% | 0%
|  | Expertise engaged Aboriginal lens | Engage FNIM knowledge sharing | Quarterly - Annually | 15% | 15%
KNOWLEDGE DEVELOPMENT AND EXCHANGE | Develop comprehensive research and KE Strategy |  | Support coordinated CSH research agenda |  | 20% | 20%
|  | Journals scan | ID research needs and gaps | Quarterly | 20% | 20%
|  | Funders' scan |  | Quarterly | 15% | 15%
|  | SHCC scan of jurisdiction work |  | Annually | 20% | 20%
|  | Annual Report section | Prioritize research needs | Annually | 30% | 30%
|  | MC, SHCC meetings; news bundles | Build KDE emerging trends | Monthly | 25% | 25%
|  | Inventory of funders' priorities | Influence research funders | Annually | 0% | 0%
|  | Meetings with CIHR, SSHRC, McConnell, Lawson |  | 1/funder org. | 10% | 10%
|  | Inventory of research institutes/ teams working in CSH~ | Influence researchers | Annually | 0% | 0%
|  | Meetings with research teams |  | 1/research team | 50% | 50%
|  | Inventory of researchers in schools | Influence student survey cohesion | Available | 60% | 60%
|  | Inventory of school survey questions |  | Possibly available | 20% | 20%
|  | Current project | Explore >research opps for CIM | 2016 | 50% | 50%
|  | Next steps projections (possible equity lens?) |  | Annually | 15% | 15%
|  | Link with research funders, researchers inventories, above | Encourage wellness-success linked research | Annually | 20% | 20%
|  |  | Support policy, practice through KE |  | 20% | 20%
|  | CBNs, Common messages | Explore opps to use HBSC, EDI data results | ~1/instrument | 15% | 15%
|  | Social media sharing |  | 2016 | 20% | 20%
|  | Comms with partners |  | Annually | 15% | 15%
|  | MC, SHCC meetings |  | Annually | 20% | 20%
|  | MC, SHCC meetings | Increase use, promo JCSH tools | 4/year | 20% | 20%
|  | Conferences |  | ~4/year | 25% | 25%
|  | Meetings with partners |  | ~4/year | 25% | 25%
|  | Testimonials on website (Start with HSP, PMH, ~YE) |  | ~10/year | 15% | 15%
|  | Stories map (Start with media, partners stories) |  | ~10/year | 25% | 25%
|  | HSP marketing - infographics, testimonials | Support evidence-informed CSH practice | 2016 | 20% | 20%
|  | Stories map, social media | Disseminate CSH implementation research | ~Quarterly | 20% | 20%
|  | MC, SHCC meetings | KT learning through sharing practices | Monthly | 20% | 20%
|  | Stories map, social media |  | ~Quarterly | 10% | 10%
|  | News bundles, newsletters | Develop resources, supports for KE in PTs | Monthly | 25% | 25%
CAPACITY BUILDING | Promote PT efficiencies, effectiveness through CSH tools, resources | Equity lens added to tools revisions | Explore adapts for existing tools | Notes in Revisions discussions | 20% | 20%
|  | HSP, PMH, YE interviews | Share promising practices' use of JCSH tools | Annually | 20% | 20%
| Promote PT efficiencies, effectiveness through KDE across sectors, PTs | Wellness Education Working Group | Develop and hold meetings | ~Quarterly | 20% | 20%
|  | Environmental scan | Curricula renewal sharing | Annually (updates) | 30% | 30%
|  | Environmental scan; CSH Highlights | Share international CSH curricula work | Annually | 15% | 15%
|  | Wellness education resources, CIM, CSH Highlights, news bundles, social media, stories map | Share integration of CSH and curricula | ~Annually | 20% | 20%
|  | Stories map, social media, news bundles | Share implementation, application of CSH | ~10/year | 15% | 15%
| Influence external partners to adopt CSH approach in work and resource development | Meetings notes, PHE's CoP video(s) | Promote CSH with external partners | ~10/year | 20% | 20%
|  | Meeting notes, PHE's CoP video(s) | Share success stories of use of CSH framework and resources by external partners | ~10/year | 20% | 20%
MONITORING, EVALUATION, AND ACCOUNTABILITY | Develop an evaluation framework and monitoring plan encompassing JCSH scope | Evaluation Working Group | Develop and hold meetings | ~Quarterly | 25% | 25%
|  | Contract(s), Eval WG membership | Engage with eval experts | ? | 20% | 20%
|  | Plan, Monitoring | Implement ME plan, adjust | Quarterly | 15% | 15%
|  | Plan, Monitoring | ME JCSH tools, resources | Quarterly | 25% | 25%