|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SHC Action Item | Date Initiated/ Updated | Date Required By: | Status | Lead | Comments / Updates |
| 1. Environmental Scan: Bullying | June 1 2020 | June 30 2020 | In Progress | ON | Update: As of July 6 only 3 PTs have responded |
| 2. Issue Statements: Return to School; Supports for Students; Masks in Schools | May 13 2020 | May 15 2020 | Complete | ON | Update: Draft 2 of overview sent to SHCC August 6 |
| 3. Food Distribution Guidelines YT | May 12 2020 | June 9 2020 | In Progress | Ian |  |
| 4. FPTGN Food Distribution Template | May 12 2020 | June 9/August 18 2020 | In Progress | Pat | Update: Draft sent by Pat to Secretariat August 6 |
| JCSH Secretariat Action Item | Date Initiated / Updated | Date Required By / Completed : | Status | Secretariat Lead | Comments / Updates |
| 1. Issue Statements Compiled: Post-Covid supports for Students with PMCs; Masks in Schools; Canada’s and International Education Reponses to COVID-19 | May 15 2020 | July 14/August 18 2020 | Ongoing | Susan | Update: Draft 2 sent to SHCC August 6 |
| 2. Healthy School Planner:  Next Steps for HSP |  |  | In Progress | Craig/Susan | Update: Budget Decisions Required  Update: July-August: CBN on options for Planner being prepared. |
| 3. CMEC, Health priorities | May 15 2020 | June 9 2020 | In Progress | Craig |  |
| 4. Joint SHCC-MC Meeting:  Susan will discuss with John Cummings the suggestion from School Health Coordinators’ Committee of a joint meeting with Management Committee. | June 9 2020 | July 14 2020 | Complete. Further follow-up required | Susan | Update: John is asking the purpose, anticipated outcome(s) of this meeting |
| 5. Work Plan: Send out the table of summer 2020 actions to the SHCC for their review and feedback, along with both the Work Plan spreadsheet and Executive Summary. | July 14 2020 | August 18 2020 | Complete | Susan | Update: Sent to SHCC July 14 |

Legend of abbreviations:

CSH – Comprehensive School Health

JCSH – Pan-Canadian Joint Consortium for School Health

MC – Management Committee

RoD – Record of Discussion/Decision

SHC – School Health Coordinator(s)

SHCC – School Health Coordinators’ Committee

F2F – Face-to-face meeting

ToR – Terms of Reference

AB – Alberta

BC – British Columbia

MB – Manitoba

NB – New Brunswick

NL – Newfoundland and Labrador

NT – Northwest Territories

NS – Nova Scotia

NU – Nunavut

ON – Ontario

PE – Prince Edward Island

PHAC – Public Health Agency of Canada

SK – Saskatchewan

YT – Yukon

AR – Annual Report

CIM – Core Indicators and Measures

HBSC – Health Behaviour in School-aged Children

PMH – Positive Mental Health